## SDR - Program Implementation Plan

| Phase 1: |
| --- |
| Key Action Steps | Expected Timeline | Expected Outcome |
| Develop a Tier System for cities/counties to be surveyed | Completed Spring 2020 | Tier system was developed to divide the state into manageable work areas. |
| Determine Cities/Counties tier based on developed criteria. | Completed Spring 2020 | This separated the Cities/Counties into smaller manageable groups. |
| Develop online/offline application to use for subdivision review field collection. | Completed Spring 2020/ongoing with any new updates | Having an app (Collector) to input data and add/delete/update as necessary, so that the information surveyed can be collected and stored by staff. |
| Develop fire survey document for subdivisions to use during field inspection review along with the app. | Completed Spring/Summer 2020 Ongoing for updates | Allow for field inspections to occur soon and determine future edits/updates for a better consistent evaluation. |
| Phase 2: |
| Key Action Steps | Expected Timeline | Expected Outcome |
| Determine subdivisions in cities/ counties located in VHFHSZ (Very High Fire Hazard Severity Zone) / SRA (state responsibility area) that need to be reviewed. | Preexisting Subdivision Identification Completed -September 2020 (real estate data) Ongoing as new data and other means of identification are identified. | Subdivisions meeting the criteria (PRC 4290.5) were identified through real estate development information over the last 20 years. This information provided a small percentage of Subdivisions. As new data is identified through other means, subdivisions will continue to be identified and surveyed. |
| Select first county/city for review based on Tier selection and begin first field reviews. Additionally, work collaboratively with AHJ officials. | October / November 2020 | County/City meetings, subdivision identification, and surveys to be reviewed and add first (kick-off) county data to the program collection process. |
| County/City subdivisions identified and added to ArcGIS with polygons around the subdivision. | Ongoing for 2020-2021 | Polygons of subdivisions are to be outlined for field inspection staff prior to field survey. |
| Schedule meetings with local gov’t stakeholders for current survey areas. | Ongoing | Continue fostering relationships with local agencies. Allow collaboration of fire survey recommendations. |
| Phase 3: |
| Key Action Steps | Expected Timeline | Expected Outcome |
| Reevaluation and determine any needed changes/updates to the fire survey report and data collection process. | Completed: December 2020 and ongoing as necessary | After first 25 subdivisions are inspected, and data is collected. Reevaluate updates/edits to the fire survey form and/or process. |
| Determine consistent recommendations resulting from the survey and report to BOF for a review session. | January 2021 and ongoing | Have a consistent recommendation strategy for the fire survey report. |
| Develop Mailer/Post Card | February 2021 | Ease of notification process to residents providing information on their subdivision. Information provided: completion of field survey, final report findings, and information on who, where to contact with questions, etc. |
| Notify homeowners/local agencies of inspected subdivisions. | January/February 2021 for first 25 and then ongoing | Primary: Provide stakeholders with final report for input. Secondary: Provide notification to homeowners regarding inspection status and outcome. |
| Develop website link for public requests for community survey. | December 2020 – almost complete | Survey questionnaire is completed: Soon be available on the Subdivision Review Program website. |
| Finalize the development of the SDR website for department and public access. | Expected completion by end of January 2021 | A website that provides consistent information related to program contact information, legislature relating to the program and public information requests for subdivision surveys. |
| Phase 4: |
| Key Action Steps | Expected Timeline | Expected Outcome |
| Reevaluation: Perform updates to the Fire Survey Report and/or process. | Ongoing | Every 25 Subdivision surveys: Reevaluate and provide needed updates based off field experience and suggestions. |
| Phase 5: |
| Key Action Steps | Timeline | Expected Outcome |
| Subdivision Development evaluation: Continue and complete subdivision reviews and data collection. | Ongoing | Continuous evaluation process as subdivisions are continually being built and meet the criteria of our reviews. Pre-existing subdivisions get reevaluated every 5-years. |
| Reevaluate the continued process/collection/standardize recommendations for the subdivision survey report and field review. | Ongoing | To provide for an organized data set and evaluation for the program. |